AgriConnect Agile Implementation & Coding Plan

User Roles, Architectural Components & Sprint Roadmap

| Architecture Lead |  |
| --- | --- |
| Tech Stack Overview | Android Native (Kotlin, Room DB, WorkManager), Backend (Node.js, Express, PostgreSQL), Satellite (Google Earth Engine API) |

1. Group Team Coding & Deliverables Assignment Matrix

Each team member is assigned direct ownership of specific codebase packages, modules, and tech deliverables:

| Team Member | Module Ownership | Key Code Deliverables / Components | Primary Tech Stack |
| --- | --- | --- | --- |
| ?? | Core App Architecture & App Scaffold | Application setup, BaseRepository, Dependency Injection (Hilt/Koin), Main Navigation Host, Core Integration Orchestration. | Kotlin, Android SDK |
| ?? (Sync Engine Lead) | Offline-First Sync Engine & Logic | SyncManager.kt, SyncQueueWorker.kt (WorkManager), LastWriteWinsResolver.kt, SyncQueueItemDao.kt. | Kotlin, WorkManager, Coroutines |
| ?? (Local DB) | Local Room Persistence & Domain Schemas | AppDatabase.kt, Entities (SaleTransaction, ProduceListing, HarvestRecord, CropField), DAOs, Migrations. | Room DB, SQLite, Kotlin |
| Thabiso Elias Keitiile (Backend Lead) | Node.js REST API & PostgreSQL Backend | Express REST Controllers, PostgreSQL Schemas (migrations.sql), Google Earth Engine API Middleware, JWT Auth. | Node.js, PostgreSQL, GEE API |
| ?? (UI & State Lead) | Marketplace UI, State Machines | ProduceListingViewModel.kt (State Machine), Listing UI Screens | Jetpack Compose / XML |
| ?? (Data & Test ) | Input Validation, Data Seeding & Unit Tests | Form Validator Utilities (FormValidator.kt), Room DB Unit Tests, Mock API Seeder, Survey Feedback Engine. | JUnit, Espresso, Mockk |
| ?? (Docs & API ) | API Contracts, Reporting & Dashboard UI | OpenAPI / Swagger Specifications, Dashboard UI (DashboardViewModel.kt), Chart Rendering, Overleaf Code Embeds. | Swagger, Kotlin, Charting |

2. Role-Based Access Control (RBAC) Implementation Logic

The code enforces three distinct user roles (FARMER, FARM_EMPLOYEE, BUYER) across both the Android mobile client and the backend REST API.

A. Android Client Navigation & Feature Guard (Kotlin)

enum class UserRole { FARMER, FARM_EMPLOYEE, BUYER } data class UserSession( val userId: String, val role: UserRole, val token: String ) object PermissionGuard { fun canAccessFinancials(role: UserRole): Boolean = role == UserRole.FARMER fun canRecordFieldData(role: UserRole): Boolean = role == UserRole.FARMER ¦¦ role == UserRole.FARM_EMPLOYEE fun canAccessMarketplaceBuyer(role: UserRole): Boolean = role == UserRole.BUYER ¦¦ role == UserRole.FARMER }

B. Node.js Middleware Endpoint Guard (JavaScript)

// middleware/authRole.js const authorizeRoles = (...allowedRoles) => { return (req, res, next) => { if (!req.user ¦¦ !allowedRoles.includes(req.user.role)) { return res.status(403).json({ error: "Access Denied: Insufficient permissions for this operation." }); } next(); }; }; module.exports = authorizeRoles;

3. Sprint-by-Sprint Coding Roadmap (names assigned are not final)

[Sprint 1: Core Setup & Local DB] ➔ [Sprint 2: Sync Engine & API] ➔ [Sprint 3: Satellite & PIR] ➔ [Sprint 4: Marketplace & UI] ➔ [Sprint 5: QA & Integration]

Sprint 1: System Scaffold, Local DB & Backend Infrastructure (Weeks 1–2)

Objective: Establish repository structure, local Room persistence, and backend database schemas.

Thato: Create GitHub master repository, setup Android Gradle build files, and establish navigation graphs.

Phemelo: Implement AppDatabase.kt and define entities (SaleTransaction, ProduceListing, HarvestRecord, CropField).

Thabiso: Setup Node.js Express server, initialize PostgreSQL database tables, and establish Docker environment.

Kutlo: Write unit tests for local Room database CRUD operations (AppDatabaseTest.kt).

Sprint 2: Offline-First Synchronization Engine (Weeks 3–4)

Objective: Build background sync queuing, conflict resolution, and REST API synchronization.

Donovan: Implement SyncManager.kt and SyncQueueWorker.kt using Android WorkManager. Build LastWriteWinsResolver.kt.

Phemelo & Donovan: Create SyncQueueItem DAO and local queue observer hooks.

Thabiso: Implement /api/v1/sync/push and /api/v1/sync/pull REST endpoints in Express.

Karabo: Generate OpenAPI / Swagger API documentation for sync endpoints.

Sprint 3: Satellite NDVI Integration & PIR Access Logging (Weeks 5–6)

Objective: Implement Google Earth Engine satellite processing and PIR camera motion capture.

Thabiso: Write Google Earth Engine API middleware to query Sentinel-2 bands and calculate NDVI = (NIR - RED) / (NIR + RED).

Thato & Karabo: Build GeoJsonMapper.kt on Android to send plot boundaries and receive compressed NDVI vector alerts.

Tsholofelo: Build MotionLogger.kt handling PIR sensor input and local photo capture storage.

Sprint 4: Marketplace Module & Role-Based UI (Weeks 7–8)

Objective: Build the produce marketplace state machine, dynamic order notifications, and dashboard.

Tsholofelo: Implement ProduceListingViewModel.kt enforcing status transitions (DRAFT -> PENDING_PUBLISH -> PUBLISHED -> SOLD).

Kutlo: Build dynamic questionnaire branching logic UI for farmer vs. buyer survey inputs.

Karabo: Implement DashboardViewModel.kt aggregating sales, expenses, and crop alert metrics.

Thato: Apply PermissionGuard across all UI views to restrict FARM_EMPLOYEE from financial views.

Sprint 5: System Integration, Validation & Testing (Weeks 9–10)

Objective: Perform end-to-end integration testing, offline simulated testing, and bug fixing.

Kutlo & Donovan: Execute simulated network loss tests (verifying local queue accumulation and opportunistic sync on connection restoration).

Thabiso & Thato: Stress test backend endpoints under multi-user payload loads.

Karabo & Entire Team: Extract code snippets and testing results into master LaTeX documentation for submission to supervisor Derrick Khupe.

4. Key Verification & Code Acceptance Criteria

1. Offline Persistence: 100% of transactions created offline must persist locally without data loss across app restarts or device reboots.

2. Sync Conflict Resolution: Concurrent record updates must deterministically resolve via LastWriteWinsResolver without crashing the application.

3. Role Isolation: Attempts by FARM_EMPLOYEE accounts to query SaleTransaction endpoints or views must return HTTP 403 Forbidden / UI block.

4. NDVI Caching: Processed satellite alerts must display on-device while in Airplane Mode, displaying a "CACHED" status badge.